## Sheet1
Sprint 2 Backlog
User Story | Priority | Story Points | Tasks Involved | Assigned to | Status
As an administrator I would like to edit existing items so that I can keep the page up to date | 4 | 3 | Continue the set up of all SQL databases | Andrej & Cameron (Pair Programming) | Complete
|  |  | Add functionality to backend page to ensure adminstrator can edit the existing items | Andrej & Cameron (Pair Programming) | Complete
As an administrator I would like to add new items so that I can update page with new sustainable activities | 4 | 3 | Add functionality to backend page to ensure adminstrator can add new items | Andrej & Cameron (Pair Programming) | Complete
As tourist of Dundee I would like to see the local relevant items to my development goal on a map so that it is easy to locate | 3 | 4 | Find suitable Map API | Bernard | Complete
|  |  | Find coordinates of all current locations and compile to a table | Leia | Complete
|  |  | Add functionality of the map to the webapp | Leia & Bernard | Complete
|  |  | *Change icons to suit the item* - if time as lower priority | Leia | Move to Sprint 3
As a school user I would like the webapp to be easy to use and interesting to look at so I can learn about sustainability in my area. | 4 | 3 | Adding Bootstrap to the Webapp to make the webapp look professional and interesting | Ivan | In progress
|  |  | Ensure all interactivity is working as it should, and navigation is clear and easy to use | Ivan | In progress
As a resident in the Dundee area I would like to be able to suggest more sustainable Dundee examples so that the site can be expanded | 1 | 2 | Add a contact form which can be used to suggest more Sustainability options | Jason | Remove as API does not work with public Github