## Sheet1
User Story | Priority | Story Points | Sprint
As a user I would like to be able to select a sustainable development goal so that I can find out more information about it | 4 | 1 | 1
As a user I want to access the website from a desktop so that I have a means of accessing it | 4 | 3 | 1
As a user I would like to be able to see the local relevant items to my development goal as a list so that I can make use of them | 4 | 2 | 1
As an administrator I would like to edit existing items so that I can keep the page up to date | 4 | 3
As an administrator I would like to add new items so that I can update page with new sustainable activities | 4 | 3 | 1
As a user I want to view a list of the different global goals so that I can see what they are | 4 | 1 | 1
As a user I would like to see the local relevant items to my development goal on a map so that it is easy to locate | 3 | 4
As a user I would like to get information including contact details about specific events so that I could attend them and get in touch if required | 3 | 2 | 1
As a user I would like to be able to view the main application on a mobile device so that I can view it anywhere | 3 | 3 | 1
As a mobile user I would like to be able to see sustainable activities close to my current location so that they are easier to find | 2 | 5
As an administator I would like the ability to add users that can add/edit/remove items so that we can share responsibility of application maintenance | 2 | 4
As a mobile user I would like to be able to check into a place through social media so that I can update others on the progress of my sustainable goals | 1 | 4
As a user I would like to create a personal list of items I am interested in so that I can print this out or save it to a list of places to visit | 1 | 3
As a user I would like to be able to suggest more sustainable Dundee examples so that the site can be expanded | 1 | 2
As a user I would like to be able to select a 'tour' so that I can explore the sustainable options in Dundee | 1 | 3
As a user I would like to check in to locations and add the amount of locations I have visited on a leaderboard so that I can compare with my friends. | 1 | 4
As a user I would like access information from the open data sets through the web app so that it can help me be more sustainable | 1 | 1
48