## Sheet1
Sprint 1 Backlog
User Story | Priority | Story Points | Tasks Involved | Completed?
As a user I want to access the website from a desktop so that I have a means of accessing it | 4 | 3 | Application must be usable and complete for a desktop
Create Header and Footer of Website
Create all pages css and html, with the help of bootstrap
As a user I want to view a list of the different global goals so that I can see what they are | 4 | 1 | Have all development goals present on the home page of the website
As a user I would like to be able to select a sustainable development goal so that I can find out more information about it | 4 | 1 | Goals are interactive buttons which opens a page dedicated to selected goal
Use icons as the buttons - given in UN brief
As a user I would like to be able to see the local relevant items to my development goal as a list so that I can make use of them | 4 | 2 | Display local sustainable attractions/events/locations as a text list to user when goal is clicked
As a user I would like to get information including contact details about specific events so that I could attend them and get in touch if required | 3 | 2 | Include specific details of each event and display to user
9
Sprint Velocity based off project etsimation taking 4 weeks
Total project velocity = 38 => 9 Story Points per week